## Innovation Tracker Updated
Category | Brand | Project | Scope | Desciption | GM | iTO(mn) | Yr | DP Vol | Yr- 26 | 1st FY | SKU & Format | Trial Status | Site | Stability | Production | Primaries | Risks | Updates | Status
Hair | Sunsilk | SSK Natural 205ml | Renovation | Increased the fill level from 195ml to 205ml | 60% | 1.3 | 2026 | 68.9 | 243.21 | 255 | Shampoo | MPT-Completed | RYK | Completed | 2026-07-13 | 2026-07-27 | Scratches recurring issue | Bottles standing issue in the puck~ Procurement to present RCA from suppliers end | On-track
Hair | Sunsilk | SSK HF Ingredient Change | Renovation | L Arginine ingredient addition to the pack | N/A | N/A | 2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Production planned for new stock once pipline is consumed | Landed
Hair | Sunsilk | SSK + Tres access pack | Innovation | Affordable pricing pack | 61.2% | 0.2 | 2026 | 2.2 | 3.99 | 8 | Serums | MPT- GFS | Steg | Only SSK - Completed | 2026-09-14 | 2026-09-27 | 1) Need to look for an alternate supplier 2) Labelling supplier needs to be searched | 1)Bottles and caps at the factory, awaiting L1 report from quality 2) Caps shortage issue of 52000 vs 64000 to be arranged before production 3) PCP timelines to be pulled back 4) 5 days Holidays and additional labelling days added | Delayed
Hair | Sunsilk | Sunsillk AD Import | Innovation | Bottles import from Indonesia. To capture H&S lapsers seeking beauty benefit with AD | 25% | 1.1 | 2026 | 35.9 | 43.69 | 43.69 | Shampoo | N/A | N/A | N/A | N/A | June- Wk-3 | N/A | Stock imported from Indo | Landed
Hair | Sunsilk | SSK spicy double patta | Innovation | strategical on it consumes to additional value vs 3.5ml @ Rs 5 sachet. | 45.4% | 0.79 | 2026 |  | 289.96 | 858 | Sachet | MPT- GFS | RYK | N/A | 2026-09-05 | 2026-09-12 | N/A | Revised mechanical hard copy is awaited | On-Track
Hair | Sunsilk | Sunsilk Sable | Innovation | 100H of ​Crystal Gloss Shine - Reinventing the iconic portfolio black shine | TBD | TBD | 2027 | TBD | TBD | 14 | Serum, Shampoo and Conditioner | TBD | Steg+ RYK | TBD | TBD | TBD | High timelines of PM &RM | Reinventing the core variant black shine - kicking off with the serum( cream based texture). Business case+formulation awaited, Network needs to be firmed up | Kick-off
Hair | Sunsilk | Sunsilk Steel | Innovation | Introducing a new hair line- all new SKUs | TBD | TBD | 2027 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | All the family in the line will be imported except for shampoo- need to work over shampoo localization. Bussiness case awaited | TBD
Hair | Sunsilk | Sunsilk Elidor | Innovation | New keratine variant launch | TBD | TBD | 2027 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | New variant addition in the spicy range | TBD
Hair | Sunsilk | SSK Power shot | Innovation | launching serum sachet | TBD | TBD | 2027 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Serum in Sachet | TBD
Hair | Lifebuoy | Project Lotus (Bottle) | Innovation | Anti Dandruff shampoo bottles 90,175,370 | 60% | 2.3 | 2026 | 68.4 | 629.2 | 755.04 | Shampoo | Completed | RYK | Completed | Apr'26 | Mar'26 | N/A | Done | Landed
Hair | Lifebuoy | Project Lotus (Sachet) | Innovation | Anti Dandruff shampoo Sachet | 39% | 1.3 | 2026 | 65.2 | 505.14 | 571 | Sachet | Completed | RYK | Completed | Apr'26 | Apr'26 | N/A | Done | Landed
Hair | Lifebuoy | Project Lilly | Innovation | Prewash Mask 150ml (Herbal &Onion) | 43% | 0.6 | 2026 | 16.7 | 39.56 | 100 | Masks | Completed | Steg | Completed | 2026-07-31 | 2026-08-07 | N/A | Listing has been staring in parallel as dispatched samples received | On-Track
Hair | Lifebuoy | Lifebuoy Rosemary/Ricewater | Innovation | Introducing science elements with our natural traditional ingredients | TBD | TBD | 2027 | TBD | 0 | TBD | Shampoo | TBD | RYK | TBD | 2026-12-05 | 2026-12-12 | Bussiness Case is awaited | Bussiness case+ Formulation+ Pack matt WIP( its fragrance in formulation is not decided) | Kick-off
Hair | Clear | Clear Courage Sachet | Innovation | Clear Octo sachet deep cleanse & Cool Black 8ml & 3.5ml | 27.5% | 0.6 | 2026 | 41.4 | 0 | TBD | Sachet | Completed | RYK | Completed | Mar'26 | Mar'26 | N/A | Done | Landed
Hair | Clear | Clear Carat & Courage | Innovation | Clear import 7 variants from AR | 25% |  | 2026 |  | 0 |  | Shampoo | Completed | NIMIR | N/A | Jan'26 | Jan'26 | N/A | Launched 3 Months covered - (3rd March) | Landed
Hair | Clear |  | Innovation | Clear localization filling with imported bottles on 2 variants Deep cleanse and Shower fresh | 36% | 1.4 | 2026 |  | 0 | 113 | Shampoo | Completed | NIMIR | Completed | Apr'26 | 2026-05-12 |  | Launched (2 variants filled) | Landed
Hair | Clear |  | Innovation | Clear localization with local mould | 60% | TBD | 2026 |  | 0 | N/A | Mould | Completed | NIMIR | N/A |  | Aug'26 | N/A | Trial done and TT stage begins | Landed
Hair | Clear | Clear CSM & HF | Innovation | Addition of 02 variants cool sport menthol & Hairfall | 25% | TBD | 2026 |  | 89 | 294 | Shampoo | Completed | NIMIR | In-progress on 8-wk stability production go-ahead | Sep'26 | Oct'26 | Caffeine procuremnet status | Caffeine is now being procured through technical supplier/antalia, timelines to be confirmed. Peppermint 900g sample pack coming from symrise supplier directly by turkey help | On-Track
Hair | Clear | Clear Limited editions | NRM | New variants launching with celebrity faces on bottles | TBD | TBD | 2027 | TBD | TBD | TBD | Shampoo | TBD | RYK | TBD | TBD | TBD | TBD | Mixing up of bottles with every celebrity face in each case- need to check the capbility | TBD
Hair | Dove | Dove Dream | Innovation | 3D Change in Dove shampoo,conditioner & mask portfolio | 62.2% | 3 | 2026 |  | 0 | TBD | Shampoo and Conditioner | MPT for 200ml, 400ml completed MPT for 90ml, 660ml awaited | RYK | Completed | Aug'26 | Sep'26 | Bulk RM(fragrance) delievery might et impacted due to cyclone conditions | Trial for 200ml/ 400ml is completed report awaited for TT MCR approval for 90ml, 660ml along with 660ml pump arrival to the site RM delieveries intact. | On-Track
Hair | Dove | Dove Dior | Innovation | Addition of new variant - Bond Repair | 68.8% | 0.4 | 2026 | 7.1 | 63.04 | 94.56 | Shampoo | Completed | RYK | Completed | May'26 | May'26 | Scratches on the foil | Scratehces on foil | Landed
Hair | Dove | Dove Delaunay | Innovation | Launching of new color damage repair line | TBD | TBD | 2027 | TBD | TBD | TBD | Shampoo, Condition and Bi-phsic serum | TBD | RYK+ Steg | TBD | TBD | TBD | Bi-phasic serum supply chain Sulfate free shampoo solution | Includes Bi-phasic serum and sealer - needs global help for refrigrant supply chain - Internal calls need to be kicked off | TBD
SKIN | Ponds | Ponds SUN | Innovation | Detan FW - reduces tan in one week (new variant) | 43.6% | 0.50245 | 2026 | 10.83 | TBD | 42 | Tube | Completed | RYK | Completed | 2026-06-28 | 2026-07-05 | N/A | Launched | Landed
SKIN | Ponds | Ponds Paddlepop | Innovation | Sunscreen 50X Brightening Power for brighter skin in 7 days​ & 3X Hydration Power to instantly hydrate | 56.49% | 1.3241 | 2026 | 1.5 | TBD | 32 | Tube | TBD | Steg | Not completed | TBD | TBD | Revision of timelines | Silica air freight timeline is 3-4 wks ~ need to pull back | Delayed
SKIN | Ponds | Ponds BB Cream 23g | NRM | Brighthen skin in 7 days | 60.19% | 0.41757 | 2026 |  | TBD | 23 | Tube | MPT not started | RYK | 2 wks | 2026-11-14 | 2026-12-18 | N/A | RYK production confirmed~ Torture test will be needed. Now the artwork is revised timelines due to aw | Delayed
SKIN | Ponds | BB Cream- Big nose Sachet 7ml | NRM | Visibly Brighter Skin ​in 7 days | 28.77% | TBD | 2027 | TBD |  | 44 | Sachet | TBD | RYK or Stancose | TBD | TBD | TBD | metallic sachet cannot run at RYK | Business case approval from IRM + SU RYK but not on metallic structure at RYK- Stancose can do it but its timeline is not locked | TBD
SKIN | Ponds | BB facewash 25g | NRM | Anti Dullness Facewash designed to remove dead skin cells and give you bright skin | TBD | TBD | 2027 | TBD | TBD | TBD | Tube | TBD | RYK | TBD | TBD | TBD | TBD | TBD | TBD
SKIN | Ponds | Ponds Hydramiracle Lotions | Innovation | Premiumum lotions | TBD | TBD | 2027 | TBD | TBD | 40 | Pump Bottle | TBD | Steg | TBD | TBD | TBD | TBD | Bussiness case and Volume sign-off required to kick-off | TBD
SKIN | Ponds | PSLG CHM | NRM | Upto 72 hours hydration (formulation change) | 49.9% | 0.5 | 2026 |  | 5 | 9 | Jar | MPT-GFS | Steg | Completed | 2026-08-29 | 2026-09-19 | Carton proofing travel | RM delievered to Steg - Cartons delievered | Delayed
SKIN | Vaseline | Vaseline Voltaire | Innovation | 70x more powerful than vitamin C - Vaseline Gluta Hya | 59.8% | 1.5191 | 2026 |  | 74 | 79 | Tubes | MPT Completed | RYK | Completed | 2026-10-10 | 2026-10-27 | Bulk PM delievery by AF and SF is at risk | MPT Trial is completed PM arrival by sea and air frieght are locked but occuring simultaneoulsy however needed to pull back air frieght timelines. | Delayed
SKIN | Vaseline | Vaseline Vancouver | Innovation | Lotions Localization - 48Hr Deep Moisturization | 59.74% | 1.5086 | 2027 |  | TBD | 209 | Pump Bottle | MPT Not started | RYK | Not begin | 2027-07-02 | 2027-08-06 | N/A | Pilot (RM/ PM) à Samples arrival date STEG Pilot – Quotes, Rates, PR/ PO & lead the discussion and update. Mould PO – Raised. Capex – Initiated. confirm timelines in next NW call. STP files are received | Kick-off
SKIN | Vaseline | Vaseline Verve | Innovation | Vaseline Cloud Soft - Face Moisturizer for 10x Plumper Skin | TBD | TBD | 2027 | TBD | TBD | 32 | Jar | TBD | TBD | TBD | Q3'27 | Q3'27 | Mould required | Jar samples received - Need to finalize the sizes for sleeve making and confirmation by brands team+ Firm up the network | Kick-off
SKIN | GAL | Project Gloss | Innovation | Ultra light gel cream- glass like skin | 60.24% | 1.0114 | 2027 |  | TBD |  | Tubes, Jars, Sachet | MPT not started | RYK | Inporgress | May'27 | May'27 | Global AW awaited | Bussiness case approval done -Network kicked off- Global artwork revision needed. | Kick-off
SKIN | GAL | Access pack | NRM | 15g facewah NRM (3x multivitamin brightening) | 53.07% | 0.64732 | 2026 |  | 40 | 60 | Tube |  | RYK | Completed | Jun'26 | Jun'26 |  | Launched | Landed
SKIN | GAL | Vit.C Facewash | Innovation | 5x brightening with Vit.C | 40.82% | 0.28225 | 2026 |  | 34 | 50.9 | Tube |  | RYK | Completed | Jun'26 | June wk-23 |  | Launched
SKIN | GAL | Sun sampling sachet | NRM | Sunscreen sampling pack | N/A | N/A | 2026 |  | N/A | 500k unit samples | Sachet |  | RYK |  | 2026-08-07 | 2026-08-14 |  | Artwork link issue; revised GAL laminate aw network delayed by 6day from 18th June | Landed
SKIN | GAL | Big nose degram | NRM | 14ml to 12ml | N/A | N/A | 2026 |  | N/A | N/A | Sachet |  | RYK | Completed | N/A | N/A |  | Launched | Landed

## Sheet1
Landed
TBD
Delayed
Kick-off
On-Track